## Sheet1
SC Housing Trust Fund - Home Repair Program
Application Process Guide
Determine the age of the property - Was the property built before January 1, 1978. If yes, property is subject to Lead-Based Paint regulations.
All properties are subject to Asbestos regulations.
Steps for Repair Activity | Check the Box upon Completion
1 |  | Sponsor completes a walk-through inspection of the entire home and site to make a preliminary determination as to whether the home is eligible for the program (feasible to repair all deficiencies with available funding, residential use, etc.)
2 |  | Sponsor completes and submits the Initial Home Repair Application - Tabs (1) & (2) of Home Repair Application Checklist.
3 |  | SC Housing program coordinator reviews the Initial Application to determine preliminary eligibility.
4 |  | Once the Initial Home Repair Application is approved by SC Housing, the Sponsor is notified to engage a residential builder or home inspector to conduct a home inspection utilizing the SC Housing Essential Property Standards Checklist (HTF-2E). Sponsor is responsible for providing the Checklist and Appendix A to the inspector to use in electronic version only.
5 |  | Sponsor submits the SC Housing Essential Property Standards Checklist (HTF-2E) to SC Housing with a request for the Preliminary Scope of Work Inspection (HTF-2A) along with items identified in Tab (3) of the Home Repair Application Checklist.
6 |  | The Preliminary Scope of Work Inspection is scheduled with an SC Housing Inspector to review SC Essential Property Standards Checklist at the property to determine the scope of work and determine areas to be tested for lead, asbestos, mold, radon etc.
7 |  | If required, the Sponsor engages the services of testing firms to conduct testing for the presence of lead, asbestos, mold, and/ or radon.
8 |  | Once test results are received if necessary, the Sponsor utilizes the information provided by the testing firms to obtain quotes from contractors to remediate lead, asbestos, mold, and/or radon. Once received, all test results and quotes are submitted to SC Housing for review.
9 |  | Based upon hazardous material testing and scope of work, sponsor and contractor must notify the homeowner if they must vacate home during construction or will have access to a portion of the house restricted while work is underway.
10 |  | If lead is present in home - Sponsor is responsible for providing remediation contractor a copy of EPA’s “Small Entity Compliance Guide to Renovate Right” - (Contractor must sign Receipt of the Small Entity Compliance Guide HTF-5A) and “The Lead-Safe Certified Guide to Renovate Right” to the homeowner (Homeowner must sign acknowledge receipt of the pamphlet HTF-5C). Sponsor is responsible for providing homeowner copies of all pre-renovation test results. Homeowner must sign acknowledge receipt of all reports HTF-5B "Pre-Renovation Hazardous Material Receipt"
11 |  | Sponsor must submit the Full Application including Tabs (4, 5 & 6) of the Home Repair Application Checklist - submit all invoices, inspections, test results, quotes, work-write ups, licenses, certifications and insurance certificates for all work completed for SC Housing review. (May require another inspection.)
12 |  | Once the Scope of Work Inspection is approved by SC Housing the Sponsor submit permits and paid permit receipts to program coordinator.
13 |  | Program Coordinator reviews permits to ensure they meet requirements of the project. Program coordinator will generate Agreement for Residential Repair Services, Funding Agreement and Restrictive Covenant, if applicable. Copies of all signed/recorded agreements must be returned to SC Housing before work can begin.
14 |  | Permits are posted at the project site - Requests for change orders must be submitted on (HTF-2C). Change orders must be approved and may require another inspection before proceeding. Contact SC Housing staff for approval.
15 |  | Interim & Final Construction Draws : Submit Inspection Request Form (HTF-2A), Draw Request for Payment (HTF-4A); Draw Summary Form (HTF-4B) with appropriate documentation (i.e., local building department inspection form, photos per Appendix B (Section VI);, warranty & equipment registrations, if applicable; disposal records for lead and asbestos; copies of hazardous substance clearance reports, etc.)
16 |  | After the Final Inspection for the contract is approved by SC Housing for scope of work included in contract, Sponsor may submit a final draw request using the (HTF-4A) Draw Request for Payment Form, Draw Summary Form (HTF-4B), Copy of Contractor's invoice for work completed.(repeat process if there are multiple contracts)
17 |  | After Sponsor receives payment for scope of work, Sponsor has (7) days to deliver payment to contractor. Contractor must sign Payment Certification (HTF-4C) for verification of receiving payment from Sponsor. Sponsor returns signed (HTF-4C) form to SC Housing with request for Project Delivery fee.
18 |  | Once all contractors have been paid for completed work, Sponsor may request Project Deliver Fee. Submit Draw Request for Payment (HTF-4A), Draw Summary Form (HTF-4B), Certification of Payment (HTF-4C) and copy of all cashed/cancelled checks paid to contractor(s) reflecting full payment for all construction cost along with contractor Affidavit of Release of Liens.
19 |  | Sponsor/Contractor(s) must provide the Beneficiary all warranty documents and copies of all signed documents (including all post-renovation evaluation reports conducted for remediation work Receipt of Post-Renovation Hazardous Materials Test Results (HTF-5D).